## Slide 1: Status of eval-with_errors_Z_1_40f42e80
eval-with_errors_Z_1_40f42e80
This document did not pass its own review: The caption on this page names Key Milestones, which appears in no source. Somebody will go looking for them. The caption on this page names Critical Risks, which appears in no source. Somebody will go looking for them. The caption on this page names Financial Status, which appears in no source. Somebody will go looking for them.

## Slide 2: Executive Summary
Risk | Workstream | Score | Owner | Mitigation | Status
Key talent attrition in the combined field organisat | Not Reported | Not Reported | Adeyemi | Confirm retention packages for named critica | unknown
Key talent attrition in the combined field organisation before the coverage mo | Not Reported | Not Reported | ⚠ NO OWNER | Confirm retention packages for named critical roles, bring the c | unknown
Key talent attrition in the combined field organisation before the cov | Not Reported | Not Reported | J. Adeyemi | Confirm retention packages for named critical roles, bring the cov | unknown
Key talent attrition in the combined field organisation before the coverage model is in force | WS4 Human Capital | Not Reported | J. Adeyemi | Confirm retention packages for named critical roles, bring the coverage model communication forward | unknown
Source: DellEMC_VCIO_Workstream_Status_HumanCapital_W3_2016-09-28.pptx (slide 1); DellEMC_VCIO_Weekly_Highlight_Report_W3_2016-09-30.docx (table 5); DellEMC_VCIO_SteerCo_Update_Session02_2016-09-29.pptx (slide 5); DellEMC_VCIO_SteerCo_Minutes_Session01_signed_2016-09-22.pdf (page 2).
eval-with_errors_Z_1_40f42e80 | Steering Committee
2

## Slide 3: Overall Integration Status
Dependency | From | To | Required | Status
Integration organisation transitioned to | Not Reported | Not Reported | Not Reported | in_progress
Spend cube required before logistics renegotiation can be scoped | Not Reported | Not Reported | Not Reported | in_progress
Approved legal entity structure required to fix the consolidation scope | Not Reported | Not Reported | Not Reported | at_risk
Works council conclusion required before the organisation structure rele | Not Reported | Not Reported | Not Reported | at_risk
Compensation plan design required before territory and quota alignment | Not Reported | Not Reported | Not Reported | in_progress
Entity plan required before transfer pricing documentation can begin | Not Reported | Not Reported | Not Reported | at_risk
Portfolio cross-reference required before the flagship event narrative | Not Reported | Not Reported | Not Reported | in_progress
Lease expiry analysis required before the EMEA site plan is approved | Not Reported | Not Reported | Not Reported | in_progress
Showing 8 of 9 rows.
Source: DellEMC_VCIO_Eskalation_Mailverlauf_M-07_2016-09-28.html (table 1); DellEMC_VCIO_Expertenrunde_ERP_Konsolidierung_2016-09-21.docx (table 2); DellEMC_VCIO_Expertenrunde_ERP_Konsolidierung_2016-09-21.docx (table 7); DellEMC_VCIO_Integration_Tracker_W3_2016-09-29.xlsx (sheet 'Massnahmenplan'!A5:J5); and 79 more.
eval-with_errors_Z_1_40f42e80 | Steering Committee
3

## Slide 4: Workstream Status
Not enough data
eval-with_errors_Z_1_40f42e80 | Steering Committee
4

## Slide 5: Key Milestones
All milestones are on plan
Milestone | Workstream | Planned | Forecast | Slippage | Status
Kombinierte Eroeffnungsbilanz erstellt | Not Reported | Not Reported | Not Reported | Not Reported | unknown
0 delayed of 3 | Finance | Not Reported | Not Reported | Not Reported | in_progress
1 delayed of 2 | Tax | Not Reported | Not Reported | Not Reported | at_risk
Integration organisation transitioned to run | Not Reported | Not Reported | Not Reported | Not Reported | in_progress
Legal entity rationalisation plan approved | Not Reported | Not Reported | Not Reported | Not Reported | at_risk
ERP consolidation blueprint signed off | Not Reported | Not Reported | Not Reported | Not Reported | at_risk
Harmonised sales compensation plan communicated | Not Reported | Not Reported | Not Reported | Not Reported | at_risk
Works council consultation DACH concluded | Not Reported | Not Reported | Not Reported | Not Reported | at_risk
Showing 8 of 12 rows.
Source: DellEMC_VCIO_Integration_Tracker_W3_2016-09-29.xlsx (sheet 'Meilensteine'!A8:K8); DellEMC_VCIO_Weekly_Highlight_Report_W3_2016-09-30.docx (table 3); DellEMC_VCIO_Integration_Roadmap_Day1_to_Day100_2016-09-16.pptx (slide 3); DellEMC_VCIO_SteerCo_Update_Session02_2016-09-29.pptx (slide 4).
eval-with_errors_Z_1_40f42e80 | Steering Committee
5

## Slide 6: Critical Risks and Issues
4 critical risk(s) are open and mitigated
Chart: 
| R-03 | R-04 | R-06 | R-07 | R-11 | Maintain the RAID register and apply the escalation threshold | Entity rationalisation slips and delays the transfer pricing model, creating an exposure at the first combined year end | Key talent attrition in the combined field organisation before the coverage mo | Key talent attrition in the combined field organisation before the cov | Debt service constrains discretionary integration spend below the level the plan assumes | Key talent attrition in the combined field organisation before the coverage model is in force
Score | 16 | 15 | 12 | 12 | 10
Source: DellEMC_VCIO_RACI_Matrix_Integration_Hub_2016-09-23.html (table 2); DellEMC_VCIO_RAID_Log_W3_2016-09-29.xlsx (sheet 'Issues'!A8:L8); DellEMC_VCIO_SteerCo_Minutes_Session01_signed_2016-09-22.pdf (page 2); DellEMC_VCIO_RAID_Log_W3_2016-09-29.xlsx (sheet 'Risks'!A8:M8); and 6 more.
eval-with_errors_Z_1_40f42e80 | Steering Committee
6

## Slide 7: Financial Status: synergies and budget
Integration spend is within budget
Chart: 
| Delivery cost for Rationalise marketing spend and event portfoli | Indirect procurement, addressable spend | Indirect procurement, addressable spend | Property lease and facilities cost | Warehouse and distribution operating cost | Property lease and facilities cost | Warehouse and distribution operating cost | Sales compensation, plan cost | Sales compensation, plan cost | Corporate and shared service personnel cost | Corporate and shared service personnel cost | Delivery cost for Renegotiate logistics and freight with the top
Budget | 7 | 4402 | 4402 | 903 | 628 | 903 | 628 | 1702 | 1702 | 2951 | 2951 | 21
Actual | 2 | 4310 | 4310 | 884 | 612 | 884 | 612 | 1638 | 1638 | 2874 | 2874 | 5
Forecast
Source: DellEMC_VCIO_Synergy_Tracker_W3_2016-09-28.xlsx (sheet 'Cost to Achieve'!A15:I15); DellEMC_VCIO_Synergy_Baseline_SignOff_2016-09-02.pdf (page 1); DellEMC_VCIO_Synergy_Tracker_W3_2016-09-28.xlsx (sheet 'Baseline'!A7:G7); DellEMC_VCIO_Synergy_Tracker_W3_2016-09-28.xlsx (sheet 'Baseline'!A12:G12); and 4 more.
eval-with_errors_Z_1_40f42e80 | Steering Committee
7

## Slide 8: Decisions Required
Decision | Body | Owner | Needed by | Recommendation
Mandate the integration tracker as the single source of truth for tasks, milestones and dates | Unknown | S. Lindqvist | ⚠ NO DEADLINE | Not Reported
Mandate the integration tracker as the single source of truth for tasks, m | Unknown | ⚠ NO OWNER | ⚠ NO DEADLINE | Not Reported
Confirm the works council consultation timetable in writing | Unknown | W. Kempowski | ⚠ NO DEADLINE | Not Reported
Exclude co-determined units from the first organisation announcement | Unknown | ⚠ NO OWNER | ⚠ NO DEADLINE | Not Reported
Report the ERP blueprint recovery plan with a dated forecast | Unknown | T. Bergström | ⚠ NO DEADLINE | Not Reported
Circulate the refreshed cross-workstream dependency map to all leads | Unknown | D. Okonjo | ⚠ NO DEADLINE | Not Reported
Count only Finance-validated initiatives towards secured synergy | Unknown | M. Haddad | ⚠ NO DEADLINE | Not Reported
Adopt the value prioritisation framework as the single basis for sequencing integration work | Unknown | A. Vasquez | ⚠ NO DEADLINE | Not Reported
Showing 8 of 12 rows.
Source: DellEMC_VCIO_SteerCo_Minutes_Session01_signed_2016-09-22.pdf (page 2); DellEMC_VCIO_Weekly_Highlight_Report_W3_2016-09-30.docx (table 6); DellEMC_VCIO_SteerCo_Update_Session02_2016-09-29.pptx (slide 7); DellEMC_VCIO_RACI_Matrix_Integration_Hub_2016-09-23.html (table 11).
eval-with_errors_Z_1_40f42e80 | Steering Committee
8

## Slide 9: Recommended Next Steps
Item | What it says | Value | Source
R-04 | Risk 'R-04' is in_progress, scored 15. Owned by J. Adeyemi. Mitigation: Confirm retention packages for named… | 15 | DellEMC_VCIO_RAID_Log_W3_2016-09-29.xlsx
Debt service constrains discretionary integration spend below the level the plan assumes | Risk 'Debt service constrains discretionary integration spend below the level the plan assumes' has a… | Not Reported | DellEMC_VCIO_SteerCo_Minutes_Session01_signed_2016-09-22.pdf
Key talent attrition in the combined field organisation before the coverage model is in force | Risk 'Key talent attrition in the combined field organisation before the coverage model is in force' is… | Not Reported | DellEMC_VCIO_SteerCo_Minutes_Session01_signed_2016-09-22.pdf
R-01 | Risk 'R-01' has a mitigation action but nobody is assigned to it. | Not Reported | DellEMC_VCIO_RAID_Log_W3_2016-09-29.xlsx
R-03 | Risk 'R-03' has a mitigation action but nobody is assigned to it. | Not Reported | DellEMC_VCIO_RAID_Log_W3_2016-09-29.xlsx
R-07 | Risk 'R-07' has a mitigation action but nobody is assigned to it. | Not Reported | DellEMC_VCIO_RAID_Log_W3_2016-09-29.xlsx
R-02 | Risk 'R-02' has a mitigation action but nobody is assigned to it. | Not Reported | DellEMC_VCIO_RAID_Log_W3_2016-09-29.xlsx
I-01 | Risk 'I-01' is rated high but has no mitigation action. | Not Reported | DellEMC_VCIO_RAID_Log_W3_2016-09-29.xlsx
Showing 8 of 12 rows.
Source: DellEMC_VCIO_RAID_Log_W3_2016-09-29.xlsx (sheet 'Risks'!A8:M8); DellEMC_VCIO_SteerCo_Minutes_Session01_signed_2016-09-22.pdf (page 2); DellEMC_VCIO_RAID_Log_W3_2016-09-29.xlsx (sheet 'Risks'!A5:M5); DellEMC_VCIO_RAID_Log_W3_2016-09-29.xlsx (sheet 'Risks'!A7:M7); and 6 more.
eval-with_errors_Z_1_40f42e80 | Steering Committee
9

## Slide 10: Data quality and limitations
What follows qualifies everything above it.
Item | What it says | Value | Source
Zielsystem und Migrationspfad fuer das ERP festlegen — owner | Resolved to K. Matsuda: Zielsystem und Migrationspfad fuer das ERP festlegen (owner) from… | K. Matsuda | DellEMC_VCIO_Integration_Tracker_W3_2016-09-29.xlsx
Datenpaket zur Kaufpreisallokation erstellen | Task 'Datenpaket zur Kaufpreisallokation erstellen' is marked complete but has no completion date. | Not Reported | DellEMC_VCIO_Integration_Tracker_W3_2016-09-29.xlsx
Anwendungslandschaft beider Unternehmen vollstaendig erfassen | Task 'Anwendungslandschaft beider Unternehmen vollstaendig erfassen' is marked complete but has no completion… | Not Reported | DellEMC_VCIO_Integration_Tracker_W3_2016-09-29.xlsx
Produktportfolio-Konkordanz veroeffentlichen | Task 'Produktportfolio-Konkordanz veroeffentlichen' is marked complete but has no completion date. | Not Reported | DellEMC_VCIO_Integration_Tracker_W3_2016-09-29.xlsx
Bewertung im Wertpriorisierungsrahmen veroeffentlichen | Task 'Bewertung im Wertpriorisierungsrahmen veroeffentlichen' is marked complete but has no completion date. | Not Reported | DellEMC_VCIO_Integration_Tracker_W3_2016-09-29.xlsx
Die berichtete gesicherte Synergie auf den von Finance validierten Wer | Task 'Die berichtete gesicherte Synergie auf den von Finance validierten Wer' is marked complete but has no… | Not Reported | DellEMC_VCIO_Teilprojekt_Protokoll_Finanzen_2016-09-27.docx
Die berichtete gesicherte Synergie auf den von Finance validierten Wert ab | Task 'Die berichtete gesicherte Synergie auf den von Finance validierten Wert ab' is marked complete but has… | Not Reported | DellEMC_VCIO_Wochenprotokoll_KW39_2016-10-27.docx
Die vorlaeufige Kundenzuordnung erstmals veroeffentlichen | Task 'Die vorlaeufige Kundenzuordnung erstmals veroeffentlichen' is marked complete but has no completion… | Not Reported | DellEMC_VCIO_Wochenprotokoll_KW39_2016-10-27.docx
Showing 8 of 146 rows.
Source: DellEMC_VCIO_Integration_Tracker_W3_2016-09-29.xlsx (sheet 'Massnahmenplan'!A16:J16); DellEMC_VCIO_Integration_Tracker_W3_2016-09-29.xlsx (sheet 'Massnahmenplan'!A8:J8); DellEMC_VCIO_Integration_Tracker_W3_2016-09-29.xlsx (sheet 'Massnahmenplan'!A15:J15); DellEMC_VCIO_Integration_Tracker_W3_2016-09-29.xlsx (sheet 'Massnahmenplan'!A31:J31); and 62 more.
eval-with_errors_Z_1_40f42e80 | Steering Committee
10