## Synergies
Synergy | Type | Workstream | Owner | Target | Realized | Forecast | Planned Realization Date | Confidence | Status
Procurement consolidation | Cost synergy | Procurement | Marco Rossi | 18000000 | 12400000 | 16000000 | 2026-12-31 | High | In Progress
IT license rationalization | Cost synergy | IT | Jonas Weber | 6000000 | 2100000 | 5200000 | 2027-03-31 | Medium | In Progress
Cross-sell to target customer base | Revenue synergy | Sales | Sofia Ivanova | 9000000 | 800000 | 4500000 | 2027-06-30 | Low | In Progress
Real estate footprint reduction | Cost synergy | Real Estate | Anna Schmidt | 4000000 | 0 | 3000000 |  | Medium | Not Started

## Integration Budget
Category | Budget | Actual | Committed | Forecast | Currency
External advisors | 500000 | 420000 | 60000 | 520000 | EUR
System migration | 1200000 | 950000 | 180000 | 1310000 | EUR
Retention | 800000 | 610000 | 90000 | 780000 | EUR
Total | 2500000 | 1980000 | 330000 | 2610000 | EUR