## Slide 1: Value Creation Integration Office Steering Committee, Session 02
Dell Inc. and EMC Corporation | W3 (26 - 30 September 2016) | Day 22 after Day 1 | 29 September 2016

## Slide 2: Executive Summary
Key message: the Day 100 commitment of 16 November 2016 still holds, but three workstreams now carry a delayed gate milestone and the value case is 32 percent secured against register target.
Overall status Amber | Milestones on track 15 of 18 | Open actions 30, of which 2 overdue and 2 blocked | Secured synergy USD 2410 m of USD 7252 m
What moved this week
  Value prioritisation framework scoring published and adopted as the sole basis for sequencing, per decision B-01
  Interim account ownership list published, closing the duplicate coverage issue raised in the first fortnight
  Portfolio cross-reference released ahead of the flagship event on 18 October 2016
What is off track
  WS2 Tax, WS3 IT, WS4 Human Capital each carry a delayed gate milestone
  M-07 ERP consolidation blueprint has slipped 14 days; the legacy upgrade at the target and the integration design are competing for the same architecture decisions
  M-13 works council consultation in DACH has slipped 14 days and is a legal gate, not a schedule preference
What the Steering Committee is asked to decide today
  B-07 hold the Day 100 review date and re-phase scope instead of moving the commitment, page 7
  Endorse the ERP blueprint recovery plan and the associated scope freeze, page 7

## Slide 3: Workstream Status Overview
Key message: the two workstreams that gate everything downstream, WS2 Tax and WS3 IT, are the ones in difficulty.
WS | Workstream | Lead | RAG now | RAG last | Progress | Open milestones | Overdue or blocked | Top risk | At SteerCo
WS1 | Finance | Whitfield | Green | Green | 57% | 3 | 0 | R-11 | Yes
WS2 | Tax | Devereux | Red | Amber | 32% | 2 | 2 | R-06 | Yes
WS3 | IT | Bergström | Red | Amber | 59% | 2 | 1 | R-01 | Yes
WS4 | Human Capital | Adeyemi | Red | Amber | 49% | 3 | 1 | R-04 | Yes
WS5 | Supply Chain | Matsuda | Green | Green | 37% | 2 | 0 | R-08 | No
WS6 | Go-to-Market | Kowalczyk | Green | Green | 47% | 2 | 0 | R-05 | No
WS7 | Real Estate | Ricciardi | Green | Green | 48% | 1 | 0 | R-10 | No
Reading: RAG is derived, not asserted. A workstream shows Red when a gate milestone is already delayed, Amber when a gate milestone is at risk or a severity 15 or higher risk is open, Green otherwise. Three workstreams moved to Red this week; none improved. Progress percentages come from the integration tracker, which decision B-02 makes the single source of truth. Where a workstream deck disagrees with this table, the tracker governs.

## Slide 4: Milestone Status: Day 1 to Day 100
Key message: 3 of 18 milestones are delayed and the largest single slip is 14 days, which the Day 100 date can still absorb only if scope is re-phased.
ID | Milestone | WS | Baseline | Forecast | Delta (d) | Status | Gate
M-05 | Legal entity rationalisation plan approved | WS2 | 07.10 | 14.10 | +7 | Delayed | Yes
M-07 | ERP consolidation blueprint signed off | WS3 | 07.10 | 21.10 | +14 | Delayed | Yes
M-09 | Harmonised sales compensation plan communicated | WS4 | 07.10 | 11.10 | +4 | At risk | Yes
M-13 | Works council consultation DACH concluded | WS4 | 28.10 | 11.11 | +14 | Delayed | Yes
M-01 | Day 1 legal close and brand launch executed | WS6 | 07.09 | 07.09 | 0 | Done | Yes
M-02 | Day 1 employee welcome eGuide live for all 140,000 employees | WS4 | 07.09 | 07.09 | 0 | Done | Yes
M-03 | Sales e-runbook live for 40,000+ sales professionals | WS6 | 07.09 | 07.09 | 0 | Done | Yes
M-04 | Combined opening balance sheet prepared | WS1 | 07.10 | 07.10 | 0 | On track | Yes
M-06 | Interim consolidated reporting pack produced | WS1 | 07.10 | 07.10 | 0 | On track | No
13 of 18 milestones are gate relevant. 18 October 2016 is an external fixed date and cannot move.

## Slide 5: Top Risks and Issues
Key message: 3 risks sit at or above the escalation threshold of severity 15, and two of them share the same root cause.
ID | Risk | WS | L x I | Band | Mitigation | Due | Trend
R-01 | Legacy ERP upgrade at the target collides with the integration design, delayin | WS3 | 4x3=12 | High | Freeze the legacy upgrade scope, run a joint architecture sessio | 14.10 | Increasing
R-03 | Master data quality in the supplier and material records prevents a clean migr | WS3 | 4x4=16 | High | Re-extract with a corrected field mapping, add a data quality ga | 05.10 | Stable
R-04 | Key talent attrition in the combined field organisation before the coverage mo | WS4 | 3x5=15 | High | Confirm retention packages for named critical roles, bring the c | 07.10 | Stable
R-02 | Works council consultation in Germany does not conclude before the organisatio | WS4 | 4x3=12 | Medium | Weekly alignment with the works council chair, prepare a reduced | 21.10 | Increasing
R-05 | Customer confusion during the portfolio transition depresses the net promoter | WS6 | 3x4=12 | Medium | Publish the portfolio cross-reference, brief the field with the | 11.10 | Decreasing
R-06 | Entity rationalisation slips and delays the transfer pricing model, creating a | WS2 | 3x4=12 | Medium | Escalate the entity chain review, run the transfer pricing outli | 21.10 | Increasing
R-07 | Interdependencies between workstreams are not visible to the teams that create | WS3 | 4x3=12 | Medium | Refresh the dependency map weekly, require both leads to confirm | 30.09 | Decreasing
Movement since session 01
Increasing: R-01, R-02, R-06
Decreasing: R-05, R-07, R-14
New this period: none
Register health
14 risks open, 3 at or above threshold, 6 escalated beyond the workstream.
2 critical or high dependencies are still not confirmed by both leads, contrary to decision B-03.

## Slide 6: Value Realisation Status
Key message: USD 2410 m of USD 7252 m is secured, but only USD 711 m has passed Finance validation, which is the figure decision B-06 says we report.
Synergy bucket | Init. | Target | Secured | % | FY17 in-year | Cost to achieve
Procurement | 3 | 823 | 428 | 52% | 171 | 85
IT cost | 3 | 412 | 224 | 54% | 86 | 90
Personnel | 2 | 414 | 195 | 47% | 88 | 114
Footprint | 1 | 134 | 52 | 39% | 22 | 41
Operations | 2 | 159 | 62 | 39% | 27 | 36
Revenue cross-sell | 3 | 4,680 | 1,248 | 27% | 302 | 157
Revenue pricing | 2 | 630 | 145 | 23% | 31 | 42
Total | 16 | 7,252 | 2,354 | 32% | 727 | 565
Bridge to the deal model, USD m run-rate
Line item | USD m
Deal model target | 8,000
In register | 7,252
Gap to deal model | 748
Secured, all initiatives | 2,354
Secured, Finance validated | 711
Realised to date | 121
Cost synergy target | 1,942
Revenue synergy target | 5,310
Revenue synergies are designed at roughly 2.7 times cost synergies, consistent with the ratio management stated publicly at announcement. Only USD 711 m has passed Finance validation, all of it in cost buckets; no revenue initiative has yet been validated, which is why the secured figure and the reportable figure differ by USD 1643 m. Issue I-03 records that the session 01 pack overstated this, and decision B-06 fixed the rule.

## Slide 7: Decisions Requested and Actions Carried Forward
Key message: one decision today, and the two actions still open from session 01 both sit on the critical path.
ID | Decision requested | Rationale | Proposed by | Status
B-05 | Exclude co-determined units from the first organisation announcement | German consultation is a legal gate, not a communication preference; annou | W. Kempowski | Open
B-07 | Hold the Day 100 value realisation review date and re-phase scope instead | The date is a sponsor commitment; scope is the variable that can move | A. Vasquez | Open
Actions carried forward from session 01
ID | Action | Owner | WS | Original due | Revised due | Shifts | Status
OP-01 | Circulate the refreshed cross-workstream dependency map to all leads | D. Okonjo | WS3 | 23.09 | 30.09 | 1 | In progress
OP-02 | Report the ERP blueprint recovery plan with a dated forecast | T. Bergström | WS3 | 29.09 | 29.09 | 0 | In progress
OP-03 | Confirm the works council consultation timetable in writing | W. Kempowski | WS4 | 30.09 | 30.09 | 0 | In progress
2 of 12 tracked actions are closed and 2 have been rescheduled at least once. Action OP-01 is recorded in the signed session 01 minutes against D. Okonjo; it was reassigned by e-mail after the meeting and the minutes were never amended.

## Slide 8: Appendix

## Slide 9: Appendix: Governance and Deal Reference
Source: company filings and the published advisory case study.
Name | Role | Integration mandate
Michael Dell | Chairman and CEO, Dell Technologies | Executive Sponsor
Rory Read | Chief Operating Executive, Dell | VCIO Co-Lead
Howard Elias | President and COO, EMC | VCIO Co-Lead
Lukas L. Hoebarth | Principal, Deloitte Consulting LLP | Lead Advisory Partner
Reference point | Value
Announcement | 12 October 2015
Close, Day 1 | 7 September 2016
Transaction value | USD 58 billion (headline USD 67 billion)
Consideration | USD 24.05 cash plus 0.11146 tracking shares per target share
Committed debt financing | USD 49.5 billion
Combined revenue | USD 74 billion
Employees | 140,000
Countries served | 180
Workstreams in the programme | more than 20
Announcement to close | 11 months
Sources
1. EMC Corp, Form 8-K Exhibit 99.1, filed 7 September 2016 (SEC EDGAR)
2. Deloitte Global, 'Dell, EMC, and Deloitte create the next tech icon: a technology M&A case study', deloitte.com
3. Dell Technologies press release, 7 September 2016
All operational names, figures, risks, actions and synergy values in this pack are synthetic and were constructed for testing purposes. They are internally consistent but are not a representation of what any party actually did.