## Slide 1: WS4 Human Capital: Weekly Status
Value Creation Integration Office (VCIO) | Reporting week W3 (26 - 30 September 2016) | Workstream lead J. Adeyemi | Prepared 28 September 2016
Overall RAG
Red
Progress vs. plan
49%
Milestones open
3
Overdue or blocked
1
Open risks
2
Top risk severity
15
Progress this week
ID | Task | Owner | Due | Status | %
A-031 | Publish combined organisation structure to lev | Adeyemi | 11.10 | Blocked | 65%
A-032 | Harmonise sales compensation plan design | Adeyemi | 11.10 | In progress | 55%
A-033 | Conclude works council consultation in Germany | Kempowski | 28.10 | In progress | 40%
A-034 | Confirm retention packages for named critical | Adeyemi | 07.10 | In progress | 75%
A-035 | Track welcome eGuide adoption to Day 30 | Brannigan | 07.10 | In progress | 60%
Milestones and dependencies
ID | Milestone or dependency | Baseline | Forecast | Status
M-02 | Day 1 employee welcome eGuide live for a | 07.09 | 07.09 | Done
M-09 | Harmonised sales compensation plan commu | 07.10 | 11.10 | At risk
M-13 | Works council consultation DACH conclude | 28.10 | 11.11 | Delayed
M-18 | Integration organisation transitioned to | 16.12 | 16.12 | On track
D-03 | Works council conclusion required before | - | 28.10 | At risk
D-04 | Compensation plan design required before | - | 11.10 | On track
Risks and blockers
ID | Risk | Sev | Mitigation | Owner
R-04 | Key talent attrition in the combined field organisat | 15 | Confirm retention packages for named critica | Adeyemi
R-02 | Works council consultation in Germany does not concl | 12 | Weekly alignment with the works council chai | Kempowski
Asks and escalations
Ask | Owner | Needed by | Status
Confirm the works council consultation timetable in writ | Kempowski | 30.09 | In progress
Update the role holder table after the Human Capital lea | Okonjo | 30.09 | In progress
Source: integration tracker as at 29 September 2016, decision B-02 makes it the single source of truth.