## Workplan
Task | Owner | Status | Progress % | Due Date | Workstream | Priority
Day-1 readiness checklist | Anna Schmidt | Done | 100 | 2026-06-15 | PMO | High
Migrate ERP chart of accounts | Jonas Weber | In Progress | 60 | 2026-07-31 | Finance | High
Harmonize payroll systems | Lisa Chen | In Progress | 45 | 2026-08-15 | HR | Medium
Consolidate CRM instances | Marco Rossi | Blocked | 30 | 2026-07-20 | IT | High
Define target operating model | Anna Schmidt | In Progress | 70 | 2026-07-25 | PMO | High
Customer communication plan | Sofia Ivanova | Not Started | 0 | 2026-08-01 | Sales | Medium
Rebrand office signage | Marco Rossi | In Progress | 50 | 2026-09-01 | Facilities | Low
Overall Progress: 82%

## Risk Log
Risk | Severity | Likelihood | Owner | Mitigation | Status
Key engineer attrition in target company | High | Medium | Lisa Chen | Retention bonus program approved by SteerCo | Open
ERP cutover slips past Q3 | Critical | Medium | Jonas Weber | Weekly cutover war-room; fallback to parallel run | Open
Customer churn during rebranding | Medium | Low | Sofia Ivanova | Proactive top-50 account outreach | Open

## Budget
Category | Planned | Actual | Workstream
IT integration | 1200000 | 950000 | IT
Severance & retention | 800000 | 610000 | HR
Rebranding | 300000 | 340000 | Sales
External advisors | 500000 | 420000 | PMO