## Slide 1: Value Creation Integration Office Integration Roadmap, Day 1 to Day 100
Dell Inc. and EMC Corporation | Version 2.0 | Last refreshed 16 September 2016

## Slide 2: Integration Phases and Gates
Key message: the programme has 78 days from today to Day 100 and two of the four remaining gates depend on decisions that are not yet taken.
Pre-Close
12 October 2015 to Day 1
Key activities
Regulatory clearance, clean team protocol, Day 1 readiness
Status
Value prioritisation framework agreed, e-guide and runbook built
Day 1
7 September 2016
Key activities
Legal close, brand launch, employee and sales enablement live
Status
3 of 3 Day 1 milestones achieved on the day
Day 1 to Day 30
to 7 October 2016
Key activities
Opening balance sheet, entity plan, ERP blueprint, organisation design
Status
Two gate milestones delayed, one at risk
Day 30 to Day 100
to 16 December 2016
Key activities
Coverage model live, consultation concluded, synergy wave 1 contracted
Status
Flagship event 18 October 2016 is a fixed external date
Post Day 100
Handover to run
Key activities
Integration organisation dissolved into functional ownership
Status
Open items transferred with named owners

## Slide 3: Master Milestone List
Key message: 13 of 18 milestones are gate relevant, and the critical path now runs through Tax and IT.
ID | Milestone | WS | Phase WS | Owner | Baseline | Delta | Gate | Status
M-01 | Day 1 legal close and brand launch executed | WS6 | Day 1 | L. Kowalczyk | 07.09 | 0 | Yes | Done
M-02 | Day 1 employee welcome eGuide live for all 140,000 employees | WS4 | Day 1 | J. Adeyemi | 07.09 | 0 | Yes | Done
M-03 | Sales e-runbook live for 40,000+ sales professionals | WS6 | Day 1 | L. Kowalczyk | 07.09 | 0 | Yes | Done
M-04 | Combined opening balance sheet prepared | WS1 | Day 1 to Day 30 | R. Whitfield | 07.10 | 0 | Yes | On track
M-05 | Legal entity rationalisation plan approved | WS2 | Day 1 to Day 30 | N. Devereux | 07.10 | +7 | Yes | Delayed
M-06 | Interim consolidated reporting pack produced | WS1 | Day 1 to Day 30 | R. Whitfield | 07.10 | 0 | No | On track
M-07 | ERP consolidation blueprint signed off | WS3 | Day 1 to Day 30 | T. Bergström | 07.10 | 0 | Yes | Delayed
M-08 | Single sign-on and directory federation live | WS3 | Day 1 to Day 30 | T. Bergström | 07.10 | 0 | No | On track
M-09 | Harmonised sales compensation plan communicated | WS4 | Day 1 to Day 30 | J. Adeyemi | 07.10 | +4 | Yes | At risk
M-10 | Supplier master consolidated for top 200 vendors | WS5 | Day 1 to Day 30 | K. Matsuda | 07.10 | 0 | No | On track
M-11 | Combined portfolio presented at Dell EMC World | WS6 | Day 30 to Day 100 | L. Kowalczyk | 18.10 | 0 | Yes | On track
M-12 | Account coverage model in force for the combined field | WS6 | Day 30 to Day 100 | L. Kowalczyk | 04.11 | 0 | Yes | On track
M-13 | Works council consultation DACH concluded | WS4 | Day 30 to Day 100 | B. Steinmüller | 28.10 | +14 | Yes | Delayed
M-14 | Site consolidation plan approved for EMEA | WS7 | Day 30 to Day 100 | F. Ricciardi | 18.11 | 0 | No | On track
M-15 | Transfer pricing model for the combined group agreed | WS2 | Day 30 to Day 100 | N. Devereux | 25.11 | 0 | Yes | On track
M-16 | Procurement synergy wave 1 contracts renegotiated | WS5 | Day 30 to Day 100 | K. Matsuda | 02.12 | 0 | Yes | On track
M-17 | Day 100 value realisation review delivered to the sponsor | WS1 | Day 30 to Day 100 | D. Okonjo | 16.12 | 0 | Yes | On track
M-18 | Integration organisation transitioned to run | WS4 | Post Day 100 | D. Okonjo | 16.12 | 0 | No | On track
This roadmap was last refreshed on 16 September 2016. Milestone forecasts move faster than this document; the integration tracker carries the current forecast.

## Slide 4: Cross-Workstream Dependencies
Key message: 2 critical or high dependencies are still unconfirmed by both leads, which decision B-03 was meant to eliminate.
ID | Deliverable handed over | From | To | Needed by | Criticality | Both leads confirmed | Status
D-01 | Approved legal entity structure required to fix the consolidation scope | WS2 | WS1 | 12.10 | Critical | No | At risk
D-02 | ERP target system decision required before the material master re-extrac | WS3 | WS5 | 03.10 | Critical | Yes | Delayed
D-03 | Works council conclusion required before the organisation structure rele | WS4 | WS4 | 28.10 | Critical | Yes | At risk
D-04 | Compensation plan design required before territory and quota alignment | WS4 | WS6 | 11.10 | High | Yes | On track
D-05 | Spend cube required before logistics renegotiation can be scoped | WS5 | WS5 | 14.10 | High | Yes | On track
D-06 | Lease expiry analysis required before the EMEA site plan is approved | WS7 | WS7 | 21.10 | Medium | Yes | On track
D-07 | Entity plan required before transfer pricing documentation can begin | WS2 | WS2 | 12.10 | High | No | At risk
D-08 | Portfolio cross-reference required before the flagship event narrative | WS6 | WS6 | 11.10 | High | Yes | On track
The advisory team identified interdependencies between workstreams as the defining challenge of a programme of this size: individuals in each workstream understand their own responsibilities but may not see how their activities land on others. This register exists to make that visible, and decision B-03 requires both sides of every handover to confirm the date. Two entries still show one-sided confirmation.