# IT Workstream — Weekly Status Report

Workstream: Information Technology

Lead: Jonas Weber

Reporting period: week 27, 2026

## Progress

Overall progress: 41%. The ERP cutover remains the critical path item.

## Achievements

Completed the network integration design.

Migrated 14 of 40 systems to the target estate.

## Risks and Issues

Risk: ERP cutover slips past Q3. Impact: High. Owner: Jonas Weber.

## Decisions

Decision: Approve parallel-run fallback for the ERP cutover weekend.

## Actions

Action: Re-baseline the cutover plan -> Jonas Weber

Action: Confirm VPN capacity uplift with the vendor -> Marco Rossi

## Support needed

Finance must sign off the chart of accounts before the ERP cutover can proceed.