# Integration SteerCo — Meeting Notes, 6 July 2026

Attendees: A. Schmidt (PMO lead), J. Weber (Finance), L. Chen (HR), M. Rossi (IT), S. Ivanova (Sales)

The CRM consolidation is blocked pending the data-privacy assessment; legal review expected by 14 July.

Action: deliver data-privacy assessment for CRM merge -> Marco Rossi

Action: update synergy tracking baseline with Q2 actuals -> Jonas Weber

Action: present retention-program uptake figures at next SteerCo -> Lisa Chen

Decision: rebranding budget overrun of 40k EUR approved.

## KPIs discussed

| KPI | Value | Target | Unit |
| --- | --- | --- | --- |
| Synergies captured | 12.4 | 30 | MEUR |
| Employee attrition (target co.) | 8 | 5 | % |
| Systems migrated | 14 | 40 | count |