## Slide 1: Weekly Integration Update — Workstream Leads
Overall progress: 75% (per workstream self-reporting)
Action: finalize TSA exit plan for IT (Marco Rossi)
Action: prepare SteerCo pre-read for budget reforecast (Jonas Weber)
Action: schedule culture-integration workshops (Lisa Chen)
Milestone Day-100 review moved to 2026-08-20

## Slide 2: Milestones
Milestone | Due Date | Status | Owner
Day-1 legal close | 2026-06-01 | Done | Anna Schmidt
Day-100 review | 2026-08-20 | On Track | Anna Schmidt
ERP go-live | 2026-10-01 | At Risk | Jonas Weber