## Legend
Dell Technologies Integration - Value Creation Integration Office (VCIO)
Dell Inc. and EMC Corporation ¦ Reporting week W3 (26 - 30 September 2016) ¦ Day 22 after Day 1 ¦ Close 7 September 2016
How to use this workbook
1. One tab per RAID category: Risks, Assumptions, Issues, Dependencies.
2. A risk becomes an issue only once it has materialised. Move the row, keep the originating risk ID.
3. Severity is calculated as likelihood times impact. Do not type it.
4. Severity 15 and above escalates to the Steering Committee, per the integration charter.
5. The Summary tab calculates automatically. Do not overwrite formulas.
Conventions and assumptions
Reporting week W3 (26 - 30 September 2016), day 22 after Day 1 (7 September 2016).
Likelihood and impact scored 1 to 5. Bands: 1 to 6 Low, 8 to 12 Medium, 15 to 20 High, 25 Critical.
Date format DD.MM.YYYY throughout.
This file is the single source of truth for risks. Where a status deck or a chat thread disagrees, the entry has to be corrected here first.
Sources for the case anchoring
EMC Corp, Form 8-K Exhibit 99.1, filed 7 September 2016 (SEC EDGAR)
Deloitte Global, 'Dell, EMC, and Deloitte create the next tech icon: a technology M&A case study', deloitte.com
Dell Technologies press release, 7 September 2016
Synthetic workbook. All operational names, figures, risks and synergy values are invented and internally consistent; they are not a representation of what any party actually did.

## Risks
Risk Register
Status 29 September 2016 ¦ 14 open risks ¦ 3 at or above severity 15 ¦ Owner: Value Creation Integration Office (VCIO)
Risk ID | Risk description | Workstream | Owner | Likelihood | Impact | Severity | Band | Mitigation action | Due date | Status | Trend | Escalated to
R-01 | Legacy ERP upgrade at the target collides with the integration design, delaying the consolidation blueprint | WS3 IT | T. Bergström | 4 | 5 | 20 | High | Freeze the legacy upgrade scope, run a joint architecture session, resequence the blueprint against the Day 100 commitment | 2016-10-14 | Open | Increasing | Steering Committee
R-02 | Works council consultation in Germany does not conclude before the organisation announcement, blocking the structure release | WS4 Human Capital | W. Kempowski | 4 | 3 | 12 | Medium | Weekly alignment with the works council chair, prepare a reduced announcement scope that excludes co-determined units | 2016-10-21 | Open | Increasing | VCIO
R-03 | Master data quality in the supplier and material records prevents a clean migration dry run | WS3 IT | G. Aydin | 4 | 4 | 16 | High | Re-extract with a corrected field mapping, add a data quality gate before each migration wave | 2016-10-05 | In progress | Stable | VCIO
R-04 | Key talent attrition in the combined field organisation before the coverage model is in force | WS4 Human Capital | J. Adeyemi | 3 | 5 | 15 | High | Confirm retention packages for named critical roles, bring the coverage model communication forward | 2016-10-07 | In progress | Stable | Steering Committee
R-05 | Customer confusion during the portfolio transition depresses the net promoter score ahead of the flagship event | WS6 Go-to-Market | L. Kowalczyk | 3 | 4 | 12 | Medium | Publish the portfolio cross-reference, brief the field with the e-runbook, measure the NPS baseline before the event | 2016-10-11 | In progress | Decreasing
R-06 | Entity rationalisation slips and delays the transfer pricing model, creating an exposure at the first combined year end | WS2 Tax | N. Devereux | 3 | 4 | 12 | Medium | Escalate the entity chain review, run the transfer pricing outline in parallel rather than in sequence | 2016-10-21 | Open | Increasing | Steering Committee
R-07 | Interdependencies between workstreams are not visible to the teams that create them | WS3 IT | D. Okonjo | 4 | 3 | 12 | Medium | Refresh the dependency map weekly, require both leads to confirm every handover date in the register | 2016-09-30 | In progress | Decreasing
R-08 | Supplier renegotiation slips past the wave 1 window and the procurement synergy lands in the following financial year | WS5 Supply Chain | K. Matsuda | 3 | 3 | 9 | Medium | Open negotiations with the top 12 logistics providers before the spend cube is complete rather than after | 2016-10-28 | Open | Stable
R-09 | Two sales organisations continue to call on the same accounts before territory alignment takes effect | WS6 Go-to-Market | L. Kowalczyk | 3 | 3 | 9 | Medium | Interim account ownership list published weekly until the coverage model is in force | 2016-10-14 | In progress | Stable
R-10 | Site consolidation assumptions rest on lease data that is not yet complete for all EMEA locations | WS7 Real Estate | F. Ricciardi | 3 | 2 | 6 | Low | Complete the lease expiry analysis for the remaining sites before the plan is approved | 2016-10-21 | Open | Stable
R-11 | Debt service constrains discretionary integration spend below the level the plan assumes | WS1 Finance | R. Whitfield | 2 | 5 | 10 | Medium | Re-phase cost to achieve into the following financial year for initiatives that are not on the critical path | 2016-11-04 | Open | Stable | Steering Committee
R-12 | Reporting arrives at the office in six different formats and reconciliation consumes the analyst capacity that should go into analysis | WS1 Finance | S. Lindqvist | 5 | 2 | 10 | Medium | Mandate the tracker as the single source, accept slide input only as commentary | 2016-10-07 | In progress | Stable
R-13 | Pension obligation at the target is larger than the baseline assumes | WS1 Finance | R. Whitfield | 2 | 4 | 8 | Medium | Commission an actuarial review before the opening balance sheet is finalised | 2016-10-07 | Open | Stable
R-14 | Rebranding at customer-facing sites is not complete before the flagship event | WS7 Real Estate | F. Ricciardi | 2 | 2 | 4 | Low | Prioritise tier 1 sites and event venues, accept a phased schedule elsewhere | 2016-10-14 | In progress | Decreasing

## Assumptions
Assumption Register
Assumptions the plan depends on and their validation status, 29 September 2016
Assumption ID | Assumption | Workstream | Date made | Impact if invalid | Validation action | Validate by | Validation status
AS-01 | The legacy ERP maintenance agreement at the target can be exited on three months notice | WS3 IT | 2016-08-12 | ERP decommissioning slips by up to nine months and the licence synergy in S-04 is lost | Legal to review the maintenance clause and confirm the notice period | 2016-10-07 | Open
AS-02 | No further regulatory condition applies to the EMEA entity mergers | WS2 Tax | 2016-08-19 | Entity rationalisation and the transfer pricing model both slip | External counsel to confirm per jurisdiction | 2016-10-14 | Open
AS-03 | Retention acceptance among named critical roles will exceed 85 percent | WS4 Human Capital | 2016-08-26 | Coverage model and account continuity are both exposed | Track acceptance weekly and report at Day 30 | 2016-10-07 | Open
AS-04 | Supplier contracts contain no change of control clause that blocks renegotiation | WS5 Supply Chain | 2016-09-02 | Procurement synergy wave 1 cannot be booked in the current financial year | Contract review for the top 12 logistics providers | 2016-10-14 | Confirmed
AS-05 | The flagship event date of 18 to 20 October is immovable | WS6 Go-to-Market | 2016-08-05 | Portfolio and narrative milestones lose their forcing function | None, treated as fixed | 2016-09-07 | Confirmed
AS-06 | Integration spend approved at close remains available in full | WS1 Finance | 2016-09-07 | Cost to achieve must be re-phased and synergy delivery moves right | Confirm with treasury at the first combined quarter end | 2016-10-21 | Open

## Issues
Issue Log
Risks that have materialised and problems already occurring, 29 September 2016
Issue ID | Issue description | Originating risk | Date raised | Workstream | Owner | Severity | Impact on milestone | Resolution action | Target date | Status | Escalated to
I-01 | Material master extract from the target is incomplete; 18 percent of records are missing mandatory fields | R-03 | 2016-09-22 | WS3 IT | G. Aydin | High | M-07 blueprint sign-off | Re-extract with corrected field mapping and a data quality gate | 2016-10-05 | In progress | VCIO
I-02 | The EMEA entity chain tax review has passed its due date and now blocks the rationalisation plan | R-06 | 2016-09-26 | WS2 Tax | N. Devereux | High | M-05 entity plan approval | Escalated to the Steering Committee with a named completion date | 2016-10-03 | Open | Steering Committee
I-03 | Reported secured synergy exceeded the Finance-validated figure in the session 01 pack | - | 2016-09-15 | WS1 Finance | M. Haddad | Medium | Credibility of the value case | Only Finance-validated initiatives are counted from session 02 onward, per decision B-06 | 2016-09-28 | Resolved
I-04 | Two field organisations called on the same 40 named accounts in the first fortnight | R-09 | 2016-09-19 | WS6 Go-to-Market | L. Kowalczyk | Medium | Customer experience ahead of the flagship event | Interim account ownership list published weekly | 2016-09-26 | Resolved
I-05 | The role holder table still names the previous Human Capital workstream lead | - | 2016-09-20 | WS4 Human Capital | D. Okonjo | Low | Ownership clarity | Update the role holder table and reconcile it against the role cards | 2016-09-30 | In progress

## Dependencies
Dependency Register
Cross-workstream handovers ¦ decision B-03 requires both leads to confirm ¦ 2 still one-sided
Dependency ID | Deliverable handed over | From workstream | From owner | To workstream | To owner | Needed by | Criticality | Both leads confirmed | Status
D-01 | Approved legal entity structure required to fix the consolidation scope | WS2 Tax | N. Devereux | WS1 Finance | R. Whitfield | 2016-10-12 | Critical | No | At risk
D-02 | ERP target system decision required before the material master re-extract | WS3 IT | T. Bergström | WS5 Supply Chain | K. Matsuda | 2016-10-03 | Critical | Yes | Delayed
D-03 | Works council conclusion required before the organisation structure release | WS4 Human Capital | J. Adeyemi | WS4 Human Capital | J. Adeyemi | 2016-10-28 | Critical | Yes | At risk
D-04 | Compensation plan design required before territory and quota alignment | WS4 Human Capital | J. Adeyemi | WS6 Go-to-Market | L. Kowalczyk | 2016-10-11 | High | Yes | On track
D-05 | Spend cube required before logistics renegotiation can be scoped | WS5 Supply Chain | K. Matsuda | WS5 Supply Chain | K. Matsuda | 2016-10-14 | High | Yes | On track
D-06 | Lease expiry analysis required before the EMEA site plan is approved | WS7 Real Estate | F. Ricciardi | WS7 Real Estate | F. Ricciardi | 2016-10-21 | Medium | Yes | On track
D-07 | Entity plan required before transfer pricing documentation can begin | WS2 Tax | N. Devereux | WS2 Tax | N. Devereux | 2016-10-12 | High | No | At risk
D-08 | Portfolio cross-reference required before the flagship event narrative | WS6 Go-to-Market | L. Kowalczyk | WS6 Go-to-Market | L. Kowalczyk | 2016-10-11 | High | Yes | On track

## Summary
RAID Summary
Calculates automatically from the four registers. No input.
Risks by severity band
Band | Number | Share
Low | 2 | 14.29%
Medium | 9 | 64.29%
High | 3 | 21.43%
Critical | 0 | 0%
Total | 14
RAID volume
Open risks | 14
Risks at or above severity 15 | 3
Risks escalated beyond the workstream | 6
Open assumptions | 4
Open issues | 3
Dependencies at risk or delayed | 4
Critical or high dependencies not confirmed by both leads | 2