## Legend
Dell Technologies Integration - Value Creation Integration Office (VCIO)
Dell Inc. and EMC Corporation ¦ Reporting week W3 (26 - 30 September 2016) ¦ Day 22 after Day 1 ¦ Close 7 September 2016
How to use this workbook
1. Baseline is locked and read only. It was signed off before Day 1.
2. Synergy Register: one row per initiative. Target, secured and realised are entered per initiative, never at bucket level.
3. Only Finance-validated initiatives count towards the reportable secured figure, per Steering Committee decision B-06.
4. Phasing carries the in-year effect for the current financial year and cross-checks back to the register.
5. Summary rolls up by bucket and reconciles to the deal model. No input.
Conventions and assumptions
Reporting week W3 (26 - 30 September 2016), day 22 after Day 1.
All amounts in USD million unless the column header says otherwise.
Run-rate is the annualised effect once fully implemented. In-year is the effect landing in the current financial year.
Baseline source: synergy baseline sign-off dated 2 September 2016, locked.
Revenue synergies are designed at roughly three times cost synergies, consistent with the ratio management stated publicly at announcement. The absolute values are synthetic.
Where this file and a status deck disagree, the Finance-validated figure here governs.
Sources for the case anchoring
EMC Corp, Form 8-K Exhibit 99.1, filed 7 September 2016 (SEC EDGAR)
Deloitte Global, 'Dell, EMC, and Deloitte create the next tech icon: a technology M&A case study', deloitte.com
Dell Technologies press release, 7 September 2016
Synthetic workbook. All operational names, figures, risks and synergy values are invented and internally consistent; they are not a representation of what any party actually did.

## Baseline
Locked Financial Baseline
Baseline as at Day 1 (7 September 2016) ¦ signed off 2 September 2016 ¦ do not edit
Baseline ID | Line item | Entity | Cost category | FY16 actual (USD m) | FY17 budget (USD m) | Source document
BL-01 | External IT maintenance and software licences | EMC Corporation | IT cost | 1840 | 1912 | Target FY16 statutory accounts, note 14
BL-02 | Data centre hosting and co-location | EMC Corporation | IT cost | 742 | 768 | Target FY16 statutory accounts, note 14
BL-03 | Indirect procurement, addressable spend | Combined | Procurement | 4310 | 4402 | Combined spend cube, wave 1 extract
BL-04 | Logistics and freight | Combined | Procurement | 1965 | 2018 | Combined spend cube, wave 1 extract
BL-05 | Component sourcing, addressable bill of materials | Combined | Procurement | 6120 | 6244 | Combined spend cube, wave 1 extract
BL-06 | Corporate and shared service personnel cost | Combined | Personnel | 2874 | 2951 | Combined FY17 operating plan
BL-07 | Sales compensation, plan cost | Combined | Personnel | 1638 | 1702 | Combined FY17 operating plan
BL-08 | Property lease and facilities cost | Combined | Footprint | 884 | 903 | Combined lease register, September 2016
BL-09 | Warehouse and distribution operating cost | Combined | Operations | 612 | 628 | Combined FY17 operating plan
BL-10 | Marketing and events | Combined | Operations | 428 | 441 | Combined FY17 operating plan

## Synergy Register
Synergy Register
One row per initiative ¦ 16 initiatives ¦ status 28 September 2016 ¦ target USD 7,252 m run-rate
Initiative ID | Initiative | Bucket | Type | Workstream | Owner | Target run-rate (USD m) | Secured run-rate (USD m) | Realised to date (USD m) | Secured % | FY17 in-year (USD m) | Cost to achieve (USD m) | Status | Finance validated
S-01 | Consolidate indirect procurement onto combined contracts | Procurement | Cost | WS5 Supply Chain | K. Matsuda | 310 | 214 | 42 | 69.03% | 96 | 38 | In progress | Yes
S-02 | Renegotiate logistics and freight with the top 12 providers | Procurement | Cost | WS5 Supply Chain | K. Matsuda | 245 | 118 | 0 | 48.16% | 44 | 21 | In progress | Yes
S-03 | Consolidate component sourcing across the combined bill of materials | Procurement | Cost | WS5 Supply Chain | K. Matsuda | 268 | 96 | 0 | 35.82% | 31 | 26 | Approved | No
S-04 | Rationalise overlapping enterprise software licences | IT cost | Cost | WS3 IT | T. Bergström | 186 | 141 | 28 | 75.81% | 62 | 34 | In progress | Yes
S-05 | Consolidate data centre footprint and hosting contracts | IT cost | Cost | WS3 IT | T. Bergström | 152 | 61 | 0 | 40.13% | 18 | 44 | Approved | No
S-06 | Merge service desk and IT operations tooling | IT cost | Cost | WS3 IT | T. Bergström | 74 | 22 | 0 | 29.73% | 6 | 12 | Business case | No
S-07 | Remove duplicated corporate and shared service functions | Personnel | Cost | WS4 Human Capital | J. Adeyemi | 296 | 148 | 31 | 50% | 74 | 96 | In progress | Yes
S-08 | Harmonise sales compensation and reduce plan complexity | Personnel | Cost | WS4 Human Capital | J. Adeyemi | 118 | 47 | 0 | 39.83% | 14 | 18 | Approved | No
S-09 | Consolidate offices where both groups hold leases in one city | Footprint | Cost | WS7 Real Estate | F. Ricciardi | 134 | 52 | 9 | 38.81% | 22 | 41 | In progress | Yes
S-10 | Consolidate warehouse and distribution network in EMEA and APJ | Operations | Cost | WS5 Supply Chain | K. Matsuda | 97 | 24 | 0 | 24.74% | 8 | 29 | Business case | No
S-11 | Rationalise marketing spend and event portfolio | Operations | Cost | WS6 Go-to-Market | L. Kowalczyk | 62 | 38 | 11 | 61.29% | 19 | 7 | In progress | Yes
S-12 | Cross-sell infrastructure portfolio into the client installed base | Revenue cross-sell | Revenue | WS6 Go-to-Market | L. Kowalczyk | 2240 | 610 | 0 | 27.23% | 148 | 74 | In progress | No
S-13 | Cross-sell client portfolio into the enterprise installed base | Revenue cross-sell | Revenue | WS6 Go-to-Market | L. Kowalczyk | 1680 | 405 | 0 | 24.11% | 96 | 61 | In progress | No
S-14 | Attach services and support to the combined portfolio | Revenue cross-sell | Revenue | WS6 Go-to-Market | L. Kowalczyk | 760 | 233 | 0 | 30.66% | 58 | 22 | Approved | No
S-15 | Extend mid-market coverage using the combined field | Revenue pricing | Revenue | WS6 Go-to-Market | L. Kowalczyk | 420 | 84 | 0 | 20% | 17 | 33 | Business case | No
S-16 | Harmonise discount governance across the combined portfolio | Revenue pricing | Revenue | WS6 Go-to-Market | R. Whitfield | 210 | 61 | 0 | 29.05% | 14 | 9 | Approved | No
| Total |  |  |  |  | 7252 | 2354 | 121 | 32.46% | 727 | 565

## Phasing
In-Year Phasing, current financial year
Monthly in-year effect per initiative in USD million, cross-checked against the register
Initiative ID | Initiative | Sep 16 | Oct 16 | Nov 16 | Dec 16 | Jan 17 | Feb 17 | Total | Check vs. register
S-01 | Consolidate indirect procurement onto combined con | 0 | 6 | 13 | 19 | 26 | 32 | 96 | ok
S-02 | Renegotiate logistics and freight with the top 12 | 0 | 3 | 6 | 9 | 12 | 14 | 44 | ok
S-03 | Consolidate component sourcing across the combined | 0 | 2 | 4 | 6 | 8 | 11 | 31 | ok
S-04 | Rationalise overlapping enterprise software licenc | 0 | 4 | 8 | 12 | 17 | 21 | 62 | ok
S-05 | Consolidate data centre footprint and hosting cont | 0 | 1 | 2 | 4 | 5 | 6 | 18 | ok
S-06 | Merge service desk and IT operations tooling | 0 | 0 | 1 | 1 | 2 | 2 | 6 | ok
S-07 | Remove duplicated corporate and shared service fun | 0 | 5 | 10 | 15 | 20 | 24 | 74 | ok
S-08 | Harmonise sales compensation and reduce plan compl | 0 | 1 | 2 | 3 | 4 | 4 | 14 | ok
S-09 | Consolidate offices where both groups hold leases | 0 | 1 | 3 | 4 | 6 | 8 | 22 | ok
S-10 | Consolidate warehouse and distribution network in | 0 | 1 | 1 | 2 | 2 | 2 | 8 | ok
S-11 | Rationalise marketing spend and event portfolio | 0 | 1 | 3 | 4 | 5 | 6 | 19 | ok
S-12 | Cross-sell infrastructure portfolio into the clien | 0 | 10 | 20 | 30 | 39 | 49 | 148 | ok
S-13 | Cross-sell client portfolio into the enterprise in | 0 | 6 | 13 | 19 | 26 | 32 | 96 | ok
S-14 | Attach services and support to the combined portfo | 0 | 4 | 8 | 12 | 15 | 19 | 58 | ok
S-15 | Extend mid-market coverage using the combined fiel | 0 | 1 | 2 | 3 | 5 | 6 | 17 | ok
S-16 | Harmonise discount governance across the combined | 0 | 1 | 2 | 3 | 4 | 4 | 14 | ok
| Total in-year effect | 0 | 47 | 98 | 146 | 196 | 240 | 727

## Cost to Achieve
Cost to Achieve
One-off cost required to deliver each initiative ¦ total USD 565 m
CTA ID | Initiative ID | Cost item | Cost type | Owner | Budgeted (USD m) | Committed (USD m) | Spent (USD m) | Remaining (USD m)
CTA-01 | S-01 | Delivery cost for Consolidate indirect procurement onto combined | Internal effort | K. Matsuda | 38 | 27 | 10 | 28
CTA-02 | S-02 | Delivery cost for Renegotiate logistics and freight with the top | Internal effort | K. Matsuda | 21 | 15 | 5 | 16
CTA-03 | S-03 | Delivery cost for Consolidate component sourcing across the comb | Internal effort | K. Matsuda | 26 | 18 | 6 | 20
CTA-04 | S-04 | Delivery cost for Rationalise overlapping enterprise software li | External advisory | T. Bergström | 34 | 24 | 8 | 26
CTA-05 | S-05 | Delivery cost for Consolidate data centre footprint and hosting | External advisory | T. Bergström | 44 | 31 | 11 | 33
CTA-06 | S-06 | Delivery cost for Merge service desk and IT operations tooling | External advisory | T. Bergström | 12 | 8 | 3 | 9
CTA-07 | S-07 | Delivery cost for Remove duplicated corporate and shared service | Severance | J. Adeyemi | 96 | 67 | 24 | 72
CTA-08 | S-08 | Delivery cost for Harmonise sales compensation and reduce plan c | Severance | J. Adeyemi | 18 | 13 | 4 | 14
CTA-09 | S-09 | Delivery cost for Consolidate offices where both groups hold lea | Site exit | F. Ricciardi | 41 | 29 | 10 | 31
CTA-10 | S-10 | Delivery cost for Consolidate warehouse and distribution network | Internal effort | K. Matsuda | 29 | 20 | 7 | 22
CTA-11 | S-11 | Delivery cost for Rationalise marketing spend and event portfoli | Internal effort | L. Kowalczyk | 7 | 5 | 2 | 5
CTA-12 | S-12 | Delivery cost for Cross-sell infrastructure portfolio into the c | Enablement | L. Kowalczyk | 74 | 52 | 18 | 56
CTA-13 | S-13 | Delivery cost for Cross-sell client portfolio into the enterpris | Enablement | L. Kowalczyk | 61 | 43 | 15 | 46
CTA-14 | S-14 | Delivery cost for Attach services and support to the combined po | Enablement | L. Kowalczyk | 22 | 15 | 6 | 16
CTA-15 | S-15 | Delivery cost for Extend mid-market coverage using the combined | Enablement | L. Kowalczyk | 33 | 23 | 8 | 25
CTA-16 | S-16 | Delivery cost for Harmonise discount governance across the combi | Enablement | R. Whitfield | 9 | 6 | 2 | 7
|  | Total |  |  | 565 | 396 | 139 | 426

## Summary
Synergy Summary by Bucket
Calculates automatically from the register and the cost to achieve tab. No input.
Bucket | Initiatives | Target (USD m) | Secured (USD m) | Secured % | FY17 in-year (USD m) | Cost to achieve (USD m)
Procurement | 3 | 823 | 428 | 52% | 171 | 85
IT cost | 3 | 412 | 224 | 54.37% | 86 | 90
Personnel | 2 | 414 | 195 | 47.1% | 88 | 114
Footprint | 1 | 134 | 52 | 38.81% | 22 | 41
Operations | 2 | 159 | 62 | 38.99% | 27 | 36
Revenue cross-sell | 3 | 4680 | 1248 | 26.67% | 302 | 157
Revenue pricing | 2 | 630 | 145 | 23.02% | 31 | 42
Total | 16 | 7252 | 2354 | 32.46% | 727 | 565
Reconciliation to the deal model
Deal model target (USD m run-rate) | 8000
Total target in register (USD m) | 7252
Gap to deal model (USD m) | 748
Secured, all initiatives (USD m) | 2354
Secured, Finance validated only (USD m) | 711
Difference, not yet validated (USD m) | 1643
Cost synergy target (USD m) | 1942
Revenue synergy target (USD m) | 5310
Revenue to cost ratio | 2.7343
Decision B-06: only the Finance-validated figure is reported to the Steering Committee from session 02 onward.