## Slide 1: WS3 IT: Weekly Status
Value Creation Integration Office (VCIO) | Reporting week W3 (26 - 30 September 2016) | Workstream lead T. Bergström | Prepared 28 September 2016
Overall RAG
Red
Progress vs. plan
66%
Milestones open
2
Overdue or blocked
1
Open risks
3
Top risk severity
20
Progress this week
ID | Task | Owner | Due | Status | %
A-021 | Complete application landscape inventory for b | Bergström | 23.09 | Done | 100%
A-022 | Agree the ERP target system and migration path | Bergström | 30.09 | Overdue | 60%
A-023 | Re-extract material master with corrected fiel | Aydin | 05.10 | In progress | 45%
A-024 | Migrate pilot population to federated single s | Bergström | 30.09 | In progress | 80%
A-025 | Complete network interconnect between the two | Bergström | 14.10 | In progress | 35%
Milestones and dependencies
ID | Milestone or dependency | Baseline | Forecast | Status
M-07 | ERP consolidation blueprint signed off | 07.10 | 21.10 | Delayed
M-08 | Single sign-on and directory federation | 07.10 | 07.10 | On track
D-02 | ERP target system decision required befo | - | 03.10 | Delayed
Risks and blockers
ID | Risk | Sev | Mitigation | Owner
R-01 | Legacy ERP upgrade at the target collides with the i | 20 | Freeze the legacy upgrade scope, run a joint | Bergström
R-03 | Master data quality in the supplier and material rec | 16 | Re-extract with a corrected field mapping, a | Aydin
R-07 | Interdependencies between workstreams are not visibl | 12 | Refresh the dependency map weekly, require b | Okonjo
Asks and escalations
Ask | Owner | Needed by | Status
Circulate the refreshed cross-workstream dependency map | Okonjo | 30.09 | In progress
Report the ERP blueprint recovery plan with a dated fore | Bergström | 29.09 | In progress
Add a data quality gate ahead of each migration wave | Aydin | 05.10 | In progress
Source: integration tracker as at 29 September 2016, decision B-02 makes it the single source of truth | Progress stated here is the workstream's own roll-up and is +7 points against the integration tracker.