Value Creation Integration Office - Weekly Integration Highlight Report

Dell Inc. and EMC Corporation  |  Reporting week W3 (26 - 30 September 2016)  |  Day 22 after Day 1

| Document | Weekly Integration Highlight Report |
| --- | --- |
| Programme | Dell Technologies Integration, run by the Value Creation Integration Office (VCIO) |
| Reporting period | 26 September 2016 to 30 September 2016 |
| Prepared by | P. Nakamura, VCIO Reporting Lead |
| Reviewed by | A. Vasquez, VCIO Programme Director |
| Distribution | Steering Committee, workstream leads, executive sponsor |
| Classification | Strictly confidential |
| Version and status | v1.0, issued |

# 1. Overall assessment

The programme is Amber. The Day 100 commitment of 16 December 2016 is still credible, but for the first time since close three workstreams carry a delayed gate milestone at the same time: WS2 Tax, WS3 IT, WS4 Human Capital. Two of those delays share a single root cause, which is that decisions taken outside the integration programme, namely the legacy ERP upgrade at the target and the pace of the EMEA entity review, are setting the pace of work inside it.

Nothing this week requires the Day 100 date to move. What it does require is a decision on scope, which is why B-07 is on the Steering Committee agenda for 29 September 2016.

| Overall RAG this week | Amber |
| --- | --- |
| Overall RAG last week | Green |
| Reason for the change | M-05 and M-07 both moved from at risk to delayed, and M-13 slipped 14 days |
| Milestones on track | 14 of 18 (3 complete, 3 delayed, 1 at risk) |
| Tasks | 38 tracked, 4 done, 20 in progress, 10 open, 2 overdue, 2 blocked |
| Overall progress | 49 percent, weighted mean across all tasks |
| Open risks | 14, of which 3 at or above the escalation threshold of severity 15 |
| Synergy secured | USD 2354 m of USD 7522 m register target (32 percent), of which USD 711 m is Finance validated |

# 2. Achievements this week

WS1 Finance: Produce purchase price allocation input pack (task A-004, owner R. Whitfield, closed by 28 September 2016)

WS3 IT: Complete application landscape inventory for both estates (task A-021, owner T. Bergström, closed by 23 September 2016)

WS6 Go-to-Market: Publish combined product portfolio cross-reference (task A-051, owner L. Kowalczyk, closed by 26 September 2016)

WS1 Finance: Publish the value prioritisation framework scoring (task A-071, owner M. Haddad, closed by 23 September 2016)

Steering Committee decision B-06 took effect: from session 02 onward only Finance-validated initiatives count towards secured synergy, which closed issue I-03.

# 3. Status by workstream

| WS | Workstream | Lead | RAG | Progress | Closed this week | Next due | Milestones |
| --- | --- | --- | --- | --- | --- | --- | --- |
| WS1 | Finance | R. Whitfield | Green | 57% | A-004 | A-001 | 0 delayed of 3 |
| WS2 | Tax | N. Devereux | Red | 32% | none this week | A-013 | 1 delayed of 2 |
| WS3 | IT | T. Bergström | Red | 59% | A-021 | A-023 | 1 delayed of 2 |
| WS4 | Human Capital | J. Adeyemi | Red | 49% | none this week | A-032 | 1 delayed of 4 |
| WS5 | Supply Chain | K. Matsuda | Green | 37% | none this week | A-041 | 0 delayed of 2 |
| WS6 | Go-to-Market | L. Kowalczyk | Green | 47% | A-051 | A-052 | 0 delayed of 4 |
| WS7 | Real Estate | F. Ricciardi | Green | 48% | none this week | A-061 | 0 delayed of 1 |

# 4. Deviations and delays

| ID | Milestone | WS | Owner | Baseline | Forecast | Slip (days) | Root cause and recovery |
| --- | --- | --- | --- | --- | --- | --- | --- |
| M-05 | Legal entity rationalisation plan approved | WS2 | N. Devereux | 7 October 2016 | 14 October 2016 | 7 | Slipped one week. Tax review of the EMEA entity chain is not complete. |
| M-07 | ERP consolidation blueprint signed off | WS3 | T. Bergström | 7 October 2016 | 21 October 2016 | 14 | Two weeks late. Legacy ERP upgrade at the target ran into the integrat |
| M-09 | Harmonised sales compensation plan communicated | WS4 | J. Adeyemi | 7 October 2016 | 11 October 2016 | 4 | Depends on works council consultation in DACH concluding first. |
| M-13 | Works council consultation DACH concluded | WS4 | B. Steinmüller | 28 October 2016 | 11 November 2016 | 14 | Two weeks late. Consultation under German co-determination law is a ha |

# 5. Risks at or above the escalation threshold

| ID | Risk | WS | L x I | Band | Trend | Mitigation | Owner | Due |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R-01 | Legacy ERP upgrade at the target collides with the integration design, | WS3 | 4 x 5 = 20 | High | Increasing | Freeze the legacy upgrade scope, run a joint architecture session, | T. Bergström | 14 October 2016 |
| R-03 | Master data quality in the supplier and material records prevents a cl | WS3 | 4 x 4 = 16 | High | Stable | Re-extract with a corrected field mapping, add a data quality gate | G. Aydin | 5 October 2016 |
| R-04 | Key talent attrition in the combined field organisation before the cov | WS4 | 3 x 5 = 15 | High | Stable | Confirm retention packages for named critical roles, bring the cov | J. Adeyemi | 7 October 2016 |

Escalation rule from the integration charter: severity 15 and above goes to the Steering Committee. 6 risks currently sit above the workstream level.

# 6. Decisions taken

| ID | Decision | Rationale | Body | Date | Affects | Status |
| --- | --- | --- | --- | --- | --- | --- |
| B-01 | Adopt the value prioritisation framework as the single basis for sequencin | Focus the office on the fifth of the opportunities that carries mo | Steering Committee | 15 September 2016 | all | Implemented |
| B-02 | Mandate the integration tracker as the single source of truth for tasks, m | Six reporting formats were reaching the office and reconciliation | Steering Committee | 15 September 2016 | all | In progress |
| B-03 | Require both workstream leads to confirm every cross-workstream handover d | Teams understand their own responsibilities but not how their acti | Steering Committee | 15 September 2016 | all | In progress |
| B-04 | Freeze the scope of the legacy ERP upgrade at the target until the consoli | The upgrade and the integration design were competing for the same | VCIO | 21 September 2016 | WS3, WS1, WS5 | In progress |
| B-06 | Count only Finance-validated initiatives towards secured synergy | Reported secured value was running ahead of what the baseline coul | Steering Committee | 15 September 2016 | all | Implemented |
| B-08 | Publish an interim account ownership list weekly until the coverage model | Two field organisations were calling on the same accounts | VCIO | 20 September 2016 | WS6 | Implemented |

# 7. Escalations to the Steering Committee

| ID | Requested decision | Why it needs the committee | Proposed by | Needed by |
| --- | --- | --- | --- | --- |
| B-05 | Exclude co-determined units from the first organisation announcement | German consultation is a legal gate, not a communication preference; a | W. Kempowski | 29 September 2016 |
| B-07 | Hold the Day 100 value realisation review date and re-phase scope instead | The date is a sponsor commitment; scope is the variable that can move | A. Vasquez | 29 September 2016 |

# 8. Look ahead: next two weeks

| ID | Milestone | WS | Owner | Due | Readiness | Gate |
| --- | --- | --- | --- | --- | --- | --- |
| M-04 | Combined opening balance sheet prepared | WS1 | R. Whitfield | 7 October 2016 | On track | Yes |
| M-06 | Interim consolidated reporting pack produced | WS1 | R. Whitfield | 7 October 2016 | On track | No |
| M-08 | Single sign-on and directory federation live | WS3 | T. Bergström | 7 October 2016 | On track | No |
| M-10 | Supplier master consolidated for top 200 vendors | WS5 | K. Matsuda | 7 October 2016 | On track | No |
| M-09 | Harmonised sales compensation plan communicated | WS4 | J. Adeyemi | 11 October 2016 | At risk | Yes |
| M-05 | Legal entity rationalisation plan approved | WS2 | N. Devereux | 14 October 2016 | Delayed | Yes |
| M-11 | Combined portfolio presented at Dell EMC World | WS6 | L. Kowalczyk | 28 October 2016 | On track | Yes |

The flagship customer event on 28 October 2016 is an external fixed date. Everything in the table above that carries a gate flag has to be true before it.

# 9. Annexes

Annex A: integration tracker as at 29 September 2016, xlsx

Annex B: RAID log as at 29 September 2016, xlsx

Annex C: synergy tracker as at 28 September 2016, xlsx

Annex D: Steering Committee pack session 02, 29 September 2016, pptx

Synthetic document. The case anchoring (entities, transaction value, close date, governance structure, workstream cut) follows publicly available sources. All operational names, figures, risks, decisions and synergy values are invented, internally consistent, and are not a representation of what any party actually did.